## Slide 1
01 / 02
◆ MONARCH · APC / CONTROLS UPDATE / 11 JUL 2026
The control system now runs on its own hardware
— and the engine analytics are proven.
Two milestones since the last update: (1) the control system boots with an executable GUI and fully autonomously on the cRIOs, and (2) the in-cylinder combustion analytics are validated against known-truth data (software-in-the-loop).
● VERIFIED
Autonomous deployment
Both cRIOs boot their own applications at power-on — independent of Python and the LabVIEW HMI.
Labview GUI is compiled as .EXE.
● VALIDATED VS GROUND TRUTH
Combustion analytics — Software-in-the-loop
All checks within tolerance.
IMEP, peak pressure and CA50 reproduce synthetic-truth data to ~0.001 bar / 0.1°.
● ALSO
• Deployment improved — included a self-healing loop on cRIO-9056 for error-free cold start.
• Safety characteristics tested live — Python/PC offline ⇒ safe mode (emergency shutdown activated).
• Tooling & docs — synthetic-data generator + combustion analytics comparator, all tested (171 green).
◆ Noble Thermodynamics — Argon Power Cycle
Python ⇄ LabVIEW supervisory migration

## Slide 2
02 / 02
NEXT / PATH TO FIRST FIRE
From validated bench to a motored engine.
STEP 01
● TOOL READY
Set motoring safety thresholds
Run a motored trace set through the harness to set the cylinder-pressure limits, so the spark/DI gate won't false-trip on the first crank.
STEP 02
● TURNKEY
SIL-1 — virtual crankshaft
Enable the 9049's built-in engine simulator; exercise the full sync → spark/DI → acquisition → analytics chain on hardware, no engine.
STEP 03
● THEN
Motored bench run → first fire
Cold-flow and motoring on the real engine, sensor calibration, then staged light-off — each step gated by its own bench drill.
● NEEDS FROM THE TEAM to keep the path clear
• Operating-procedure sheets — cold-start / purge / light-off / abort (the sequencing spec). • Real sensor calibrations for the 9049 cylinder-pressure channels.
• Engine physical pressure limit for the hard over-pressure trip. • Bench + second operator for the command-authority handover rehearsal.
◆ Noble Thermodynamics
Prepared 11 Jul 2026 · questions → controls